## Finance Hub GANNT
Task | Start Date | Duration | End Date
Determining Existing Fucntionality | 2017-08-01 | 5 | 2017-08-05
Determining Additional Functionality | 2017-08-06 | 5 | 2017-08-10
Initial Site Architecture Design | 2017-08-11 | 12 | 2017-08-22
Choosing Team Members | 2017-08-23 | 8 | 2017-08-30
Informing Team Members | 2017-08-31 | 1 | 2017-08-31
Clarifying Roles | 2017-09-01 | 5 | 2017-09-05
Break for Career Fair | 2017-09-06 | 2 | 2017-09-07
Basic ASP.net Training for Team Members | 2017-09-08 | 10 | 2017-09-17
Full Site Architecture Design | 2017-09-18 | 5 | 2017-09-22
Intermediate ASP.net Training for Team Members | 2017-09-23 | 9 | 2017-10-01
Initial Database Design | 2017-10-02 | 5 | 2017-10-06
Research into CAS Authorization | 2017-10-07 | 7 | 2017-10-13
Implement Authorization | 2017-10-14 | 14 | 2017-10-27
Work on Existing Functionality Part 1 | 2017-10-28 | 8 | 2017-11-04
Advanced ASP.net Training for Team Members | 2017-11-05 | 8 | 2017-11-12
Work on Existing Functionality Part 2 | 2017-11-13 | 9 | 2017-11-21
Thanksgiving Break | 2017-11-22 | 5 | 2017-11-26
Full Database Design | 2017-11-27 | 7 | 2017-12-03
Break for Finals | 2017-12-04 | 12 | 2017-12-15
Finish work on Existing Functionality | 2017-12-16 | 17 | 2018-01-01
Test Existing Functionality | 2018-01-05 | 6 | 2018-01-10
Initial New Features Architecture Design | 2018-01-11 | 6 | 2018-01-16
Work on Additional Functionality Part 1 | 2018-01-17 | 11 | 2018-01-27
Additional Functionality Database Check | 2018-01-28 | 4 | 2018-02-03
Work on Additional Functionality Part 2 | 2018-02-04 | 10 | 2018-02-13
Work on Additional Functionality Part 3 | 2018-02-14 | 15 | 2018-02-28
Test Additional Functionality | 2018-03-01 | 8 | 2018-03-08
Add Style (CSS) | 2018-03-09 | 23 | 2018-03-31
Final Tests of Finance Hub | 2018-04-01 | 20 | 2018-04-20